## Sheet1
soccer toy project
| budget | week 1 | wwek2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week 11 | week12 | week13
design prototype | 24 | soccer toy project week 1: 12; soccer toy project wwek2: 12
build protoype | 30 | soccer toy project week3: 10; soccer toy project week4: 10; soccer toy project week5: 10
order parts | 10 | soccer toy project week6: 5; soccer toy project week7: 5
prepare production | 64 | soccer toy project week6: 16; soccer toy project week7: 10; soccer toy project week8: 22; soccer toy project week9: 16
prepare marketing | 30 | soccer toy project week6: 6; soccer toy project week7: 6; soccer toy project week8: 0; soccer toy project week9: 6; soccer toy project week10: 12
assemble&test | 36 | soccer toy project week10: 18; soccer toy project week 11: 18
launch | 12 | soccer toy project week12: 12
total | 206 | 12 | 12 | 10 | 10 | 10 | 27 | 21 | 22 | 22 | 30 | 18 | 12
cumulative |  | 12 | 24 | 34 | 44 | 54 | 81 | 102 | 124 | 146 | 176 | 194 | 206
what is total cost without contingency?
206$
do you think you should add contingency.if so how much?
based on contingency buffer 5% and 10% would be better. That can be 0.1*206= 20.60$ or 0.05*206=10.30$ | bar: soccer toy project week 1 to soccer toy project week8
so adding between 10.30$ and 20.60$ would be better in my view. | bar: soccer toy project week 1 to soccer toy project week4